## Sheet1
| Risks | Risk Resolution Measures | Justistification
1 | Incomplete understanding of requirements and needs. | Keeping constant contact with OIE throughout the build. Ensure team has deep understanding of what OIE is looking for. No assuming. | Many organization who need software built don't know how software works, its capabilities and limits, and don't know how to communicate it. Need to ensure we get a deep understanding of what they ultimately need and give recommendations.
2 | Not sweating the small stuff. Overlooking things in the code and leaving obvious holes in encryped software. | Constant review and testing of encryped and secure login/logout, and personal information storing. Constant review of database measures as well. | Constantly reviewing and testing the code for obvious holes will eliminate easy access to personal information if system is hacked. Keeping a rotation of different reviewers and testers will help spot small errors.
3 | Going over budget | Management team must be made fully aware of the budget and its limits. Keep constant review of timelines/milestones and ensure they fall in line with budget. | Always keep the budget on high priority. The second management loses sight of the budget, timelines and milestones is when things take a wrong turn. If management keeps a tight leash on the process and fully understands the limits, the process should be fine.
4 | Putting too much focus on how the software looks, and not its functionality. | Functionality and convenience will be a higher priority than cosmetics. There will be a hightened focus on how fluid the system works. Users want fast results and convenient navigation. | Although cosmetics is important, ensuring users have an easy and convenient experience is more important. Difficult navigation and confusing layouts make for an unpleasant experience.
5 | Staff capabilities and shortcomings | Management will ensure constant contact and an open-door and team building environment during development. Skills and knowledge will not be something that holds a team member down. | Management fully understands that developers will have questions and skill levels will vary. Keeping and open work environment and providing proper training will ensure no one falls behind and milestones are met on time.